Construction Project Management Case Study (PMP)

Addressing Coordination Gaps Through Strong Integration Management

Industry: Construction

Primary Case Study Topic: Construction Project Management Case Study

PMP Knowledge Area Focus: Project Integration Management

Core Problem: Coordination Gaps Across Multiple Stakeholders

Target Audience: Project Directors, Senior Construction Leaders

SEO Keywords Embedded:
pmp certification training course online, project management training and certification, pmp certification cost mumbai, pmp certification cost pune

1. Case Study Introduction

Construction projects are among the most complex project environments due to their multi-stakeholder nature, regulatory constraints, parallel workstreams, and high financial exposure. While technical planning is often strong, many construction projects fail because of poor coordination and weak integration governance.

This construction project management case study is designed for learners enrolled in a PMP certification training course online and focuses on how coordination gaps can derail execution—and how Project Integration Management enables recovery.

2. Organizational Background

Skyline Developments Ltd. is a Tier-1 construction firm executing large commercial and infrastructure projects across India. The organization follows a functional structure with strong departmental autonomy.

Skyline won a contract to build a 25-storey commercial IT park in Pune with the following characteristics:

- Contract value: ₹480 Crores

- Duration: 32 months

- Location: High-density urban zone

- Compliance: Municipal, environmental, fire, and safety authorities

The project was strategically important for brand positioning and future government tenders.

3. Project Stakeholder Landscape

The project involved a highly complex stakeholder ecosystem:

- Project Director (overall accountability)

- Civil & Structural Contractor

- MEP Contractors (Electrical, Plumbing, HVAC)

- Architecture & Design Consultants

- Safety & Compliance Teams

- Procurement & Vendor Management

- Local Government Authorities

- Client Representatives

This complexity made Integration Management a critical success factor.

4. Project Objectives

The key project objectives were:

- Deliver the project within the approved timeline

- Maintain strict quality and safety compliance

- Control costs and minimize claims

- Ensure seamless coordination between contractors

- Achieve formal phase-wise approvals

Despite having experienced professionals, the project soon encountered serious issues.

5. The Core Problem: Coordination Gaps

Within the first six months, clear symptoms of poor integration began to appear.

5.1 Fragmented Planning

- Each contractor maintained separate schedules

- No consolidated master schedule existed

- Dependencies between civil, MEP, and finishing activities were unclear

5.2 Authority & Governance Breakdown

- Contractors escalated decisions directly to senior management

- The Project Director’s authority was frequently bypassed

- Decision-making became inconsistent and reactive

5.3 Uncontrolled Changes

- Design and scope changes were approved verbally

- Impact on cost and schedule was rarely assessed

- Rework increased significantly

5.4 Communication Failures

- Progress reports differed across teams

- No centralized dashboard or reporting format

- Stakeholders received conflicting status updates

5.5 Poor Monitoring & Control

- Focus was on individual work packages

- Overall project health indicators were missing

- Risks were identified late

6. Business Impact of Coordination Gaps

As coordination issues escalated, the project experienced:

- 4–5 months schedule slippage

- Cost overruns due to idle labor and rework

- Increased contractual claims from vendors

- Heightened compliance risks

- Loss of stakeholder confidence

This situation represents a classic PMP exam scenario where Integration Management is weak.

7. Integration Management Recovery Strategy (PMP-Aligned)

A PMP-certified Project Director led a structured recovery using PMBOK-aligned integration practices.

7.1 Re-Establish Project Charter Authority

- The Project Charter was formally revalidated

- Authority of the Project Director was explicitly reinforced

- Escalation and approval paths were documented

PMP Focus: Develop Project Charter

7.2 Develop an Integrated Project Management Plan

- All contractor schedules were consolidated into a master schedule

- Scope, cost, risk, quality, and communication plans were aligned

- Interdependencies were clearly mapped

PMP Focus: Develop Project Management Plan

7.3 Direct and Manage Project Work

- Weekly integrated coordination meetings were mandated

- Cross-functional decision-making replaced siloed execution

- Issues were tracked centrally

PMP Focus: Direct and Manage Project Work

7.4 Monitor and Control Project Work

- Performance dashboards tracked schedule variance and cost variance

- Risk indicators were reviewed proactively

- Corrective actions were data-driven

PMP Focus: Monitor and Control Project Work

7.5 Implement Integrated Change Control

- A formal Change Control Board (CCB) was established

- All changes required documented impact analysis

- Unauthorized changes were rejected

PMP Focus: Perform Integrated Change Control

7.6 Phase Closure and Knowledge Capture

- Phase-wise acceptance was enforced

- Lessons learned were documented and archived

- Best practices were shared across other projects

PMP Focus: Close Project or Phase

8. Results After Integration Improvement

Following the recovery actions:

- Schedule slippage was reduced to 6–8 weeks

- Cost overruns stabilized

- Contractor coordination improved significantly

- Compliance risks were mitigated

- Stakeholder confidence was restored

The project successfully moved into later phases under controlled governance.

9. Key Learnings for Project Directors

This construction project management case study PMP clearly demonstrates:

- Coordination gaps are leadership and integration failures

- Technical expertise alone does not ensure project success

- Integration Management is the backbone of construction projects

- Governance discipline is non-negotiable for Project Directors

10. PMP Exam & Career Relevance

For professionals evaluating pmp certification cost Mumbai or pmp certification cost Pune, selecting a PMP certification training course online that includes such detailed construction case studies is critical.

High-quality project management training and certification programs must teach:

- Governance enforcement

- Cross-stakeholder coordination

- Integration-based decision making

- PMP exam-oriented situational thinking

11. Conclusion

This detailed construction case study illustrates how coordination gaps can threaten even well-funded projects—and how Project Integration Management enables recovery, control, and value delivery.

For Project Directors and senior managers, mastering integration practices through real-world case studies is essential for both PMP exam success and construction project leadership excellence.