25 PMP Exam-Style Questions

Construction Project Management – Integration Management

Q1.

A construction project has multiple contractors working independently with no consolidated schedule. What should the Project Director do FIRST?

A. Ask contractors to speed up their activities
B. Develop an integrated master schedule
C. Escalate the issue to senior management
D. Replace the planning team

✅ Correct Answer: B

📘 Explanation:
The root cause is lack of integration. PMP expects the project manager to create a single integrated schedule as part of the Project Management Plan. Escalation or replacement comes later if needed.

Q2.

Design changes are being approved verbally on a construction project. What is the BEST corrective action?

A. Accept changes to maintain client satisfaction
B. Document changes after implementation
C. Establish an Integrated Change Control process
D. Ask contractors to absorb the changes

✅ Correct Answer: C

📘 Explanation:
Verbal approvals violate PMP governance. Perform Integrated Change Control ensures changes are evaluated for scope, cost, and schedule impact before approval.

Q3.

Contractors bypass the Project Director and escalate issues directly to top management. Which document should be reviewed FIRST?

A. Communications Management Plan
B. Risk Register
C. Project Charter
D. Stakeholder Register

✅ Correct Answer: C

📘 Explanation:
The Project Charter defines authority. If it is unclear, governance collapses. PMP emphasizes revalidating authority before enforcing controls.

Q4.

Multiple progress reports show conflicting project status. What should the Project Director do?

A. Accept the most optimistic report
B. Stop all reporting temporarily
C. Standardize performance reporting
D. Replace reporting teams

✅ Correct Answer: C

📘 Explanation:
PMP stresses consistent, integrated reporting under Monitor and Control Project Work. Standardization ensures one source of truth.

Q5.

Uncontrolled changes are causing cost overruns. Which process was most likely skipped?

A. Develop Schedule
B. Validate Scope
C. Perform Integrated Change Control
D. Plan Risk Management

✅ Correct Answer: C

📘 Explanation:
Cost overruns from changes indicate that change requests were not formally assessed and approved.

Q6.

The project director wants to realign all subsidiary plans into one framework. Which process applies?

A. Direct and Manage Project Work
B. Develop Project Management Plan
C. Close Project or Phase
D. Monitor and Control Project Work

✅ Correct Answer: B

📘 Explanation:
Only Develop Project Management Plan integrates all subsidiary plans into one baseline.

Q7.

Which artifact best helps identify interdependencies among contractors?

A. Risk Register
B. Work Performance Reports
C. Integrated Schedule
D. Issue Log

✅ Correct Answer: C

📘 Explanation:
An integrated schedule clearly shows dependencies across workstreams—critical in construction projects.

Q8.

A Project Director enforces weekly cross-functional coordination meetings. Which PMP process does this support?

A. Manage Communications
B. Direct and Manage Project Work
C. Develop Schedule
D. Plan Stakeholder Engagement

✅ Correct Answer: B

📘 Explanation:
Directing and managing work includes coordinating people and activities to implement the plan.

Q9.

Which indicator BEST signals weak integration?

A. High quality deliverables
B. Independent decision-making by teams
C. Strong contractor performance
D. On-time procurement

✅ Correct Answer: B

📘 Explanation:
Independent decisions without integration cause misalignment—a classic PMP red flag.

Q10.

A change request is approved without assessing schedule impact. What is the PRIMARY risk?

A. Quality degradation
B. Stakeholder dissatisfaction
C. Schedule slippage
D. Resource shortage

✅ Correct Answer: C

📘 Explanation:
Ignoring schedule impact almost always results in delays in construction projects.

Q11.

Who has the authority to approve changes after governance is restored?

A. Sponsor
B. Client
C. Change Control Board
D. Contractors

✅ Correct Answer: C

📘 Explanation:
PMP mandates formal approval through the Change Control Board (CCB).

Q12.

What tool helps the Project Director evaluate overall project health?

A. Risk Breakdown Structure
B. Performance Dashboard
C. Issue Log
D. Stakeholder Map

✅ Correct Answer: B

📘 Explanation:
Dashboards integrate schedule, cost, and risk data for holistic monitoring.

Q13.

A contractor implements an unapproved design change. What should the Project Director do NEXT?

A. Accept the change
B. Issue a penalty
C. Submit a change request for evaluation
D. Stop project work

✅ Correct Answer: C

📘 Explanation:
Even unauthorized changes must go through formal Integrated Change Control.

Q14.

Which process ensures formal phase acceptance in construction?

A. Validate Scope
B. Close Project or Phase
C. Control Quality
D. Monitor Risks

✅ Correct Answer: B

📘 Explanation:
Phase closure includes formal acceptance and documentation.

Q15.

What is the PRIMARY benefit of Integration Management in construction projects?

A. Faster procurement
B. Reduced documentation
C. Coordinated decision-making
D. Lower labor costs

✅ Correct Answer: C

📘 Explanation:
Integration aligns people, processes, and decisions—critical in complex projects.

Q16.

A project is slipping despite individual teams meeting their targets. What is the MOST likely cause?

A. Poor quality planning
B. Weak integration
C. Inadequate resources
D. Vendor delays

✅ Correct Answer: B

📘 Explanation:
Local optimization without integration causes global failure.

Q17.

Which document helps capture coordination learnings for future projects?

A. Issue Log
B. Risk Register
C. Lessons Learned Register
D. Stakeholder Register

✅ Correct Answer: C

📘 Explanation:
Lessons learned are captured during closure and reused.

Q18.

A Project Director wants to stop unauthorized approvals. What should be implemented?

A. Escalation matrix
B. Communication plan
C. Change management plan
D. Procurement strategy

✅ Correct Answer: C

📘 Explanation:
Change Management Plan defines how changes are submitted, reviewed, and approved.

Q19.

What is the BEST way to handle conflicting stakeholder expectations?

A. Prioritize client demands
B. Enforce integration governance
C. Ignore minor conflicts
D. Increase reporting frequency

✅ Correct Answer: B

📘 Explanation:
Governance through Integration Management aligns expectations.

Q20.

Which PMP process links strategy to execution?

A. Develop Schedule
B. Develop Project Charter
C. Perform Quality Assurance
D. Plan Procurement

✅ Correct Answer: B

📘 Explanation:
The charter formally authorizes and aligns the project with business goals.

Q21.

What happens if integration is weak during execution?

A. Faster delivery
B. Reduced stakeholder engagement
C. Increased rework
D. Lower documentation effort

✅ Correct Answer: C

📘 Explanation:
Lack of coordination causes rework—a common construction failure.

Q22.

Which role ensures integration across all knowledge areas?

A. Sponsor
B. Functional Manager
C. Project Manager
D. Site Engineer

✅ Correct Answer: C

📘 Explanation:
Integration is the Project Manager’s core responsibility.

Q23.

A Project Director wants to assess cumulative change impact. What should be reviewed?

A. Individual change requests
B. Risk register
C. Integrated baselines
D. Stakeholder matrix

✅ Correct Answer: C

📘 Explanation:
Baselines show total impact on scope, schedule, and cost.

Q24.

What is the PRIMARY goal of Monitor and Control Project Work?

A. Approve changes
B. Track individual performance
C. Identify variances and take action
D. Close contracts

✅ Correct Answer: C

📘 Explanation:
Monitoring focuses on variance analysis and corrective action.

Q25.

Why is Integration Management critical for PMP exam success?

A. It has the most formulas
B. It connects all PMP processes
C. It focuses only on documentation
D. It is optional in Agile projects

✅ Correct Answer: B

📘 Explanation:
Integration Management ties all knowledge areas together—PMP exam heavily tests this mindset.